## Slide 1: Dover Community Center Project
Accelerating success.
Timelines and Costs to Meet the Board of Selectmen’s Charge
  September 12, 2022
  Prepared by: Colliers Project Leaders

## Slide 2: Agenda
Review Options Requested by Board of Selectmen
  Option 1 – Rebid the project as currently designed
  Option 2 – Develop alternative facility design to meet our current budget of $18.85M ($16.65M+/- remaining)
    Option 2A – Evaluate previous options
    Option 2B – Evaluate project phasing
  Discussion

## Slide 3: Option 1 (Process): Re-Prequal & Re-Bid
Process Includes:
Prepare documentation
Perform cost estimate
Contractor prequalification
Solicit contractor bids
Review bids
Present bids to Building Committee
Present GC Award Recommendation to BOS
March 2023 Special Town Meeting for Budget Overage (assumed)

## Slide 4
Option 1: Re-Prequal & Re-Bid Timeline (5 Months to Start of Construction) and Costs
TOTAL: $340K+?**
* Additional contingency and construction / bid overage not included *
** The above values exclude construction – closeout as those phases are part of the existing OPM & Designer contracts **
***Assumes OPM and Architect are contracted by November 1, 2022***
NOV-DEC
JAN-FEB
APRIL 2023 – MAY 2024
JUNE - JULY
Docs & Prequal
STM
Bid
MARCH
Construction
Closeout

## Slide 5
Option 2 (Process): Re-Design, Re-Prequal & Re-Bid to Existing Budget
Process Includes:
Budget analysis to understand new construction budget
Re-evaluate building program
Evaluate multiple design alternatives and select a preferred option
Engage the community throughout the process
Produce new design documents: Schematic Design(SD), Design Development(DD) and Construction Documents(CD)
Perform cost estimates: SD, DD and CD
Perform value engineering
Contractor prequalification
Solicit contractor bids
Review bids
Present bids to Building Committee
Present GC Award Recommendation to BOS

## Slide 6
Option 2: Re-Design, Re-Prequal & Re-Bid to Existing Budget Timeline (15 Months to Start of Construction) and Costs
NOV 2022 – OCT 2023
NOV-DEC
FEB 2024 – MARCH 2025
APRIL - MAY
Prequal
Bid
JAN
Construction
Closeout
Design
Prequal
STM
TOTAL: $1.8M+/-?**
* Additional contingency and construction / bid overage not included *
** The above values exclude construction – closeout as those phases are part of the existing OPM & Designer contracts **
***Assumes OPM and Architect are contracted by November 1, 2022***

## Slide 7: Option 2A: Evaluate previous options (Assume increased costs and time)
  Review the project’s “program requirements” to ensure they’re relevant in a post covid world and are not provided by other organizations.
  Compare current design/costs to Pembroke Community Center & Newton Senior Center.
  Review current design to ensure that it is in fact an efficient as well as effective design - that hones closely to the community center design that was presented to and approved by the Town at the October 2019 Town meeting.
  Consider engaging an architect with extensive community center experience to review what we have. If this is what the BOS decide, they should create their own Request for Proposal to procure the services of an independent architectural service.
Option 2B: Evaluate project phasing (Assume increased costs and time)

## Slide 8
Discussion

## Slide 9
Option 1: Re-Prequal & Re-Bid Timeline and Costs
OPM: $155K+/-*
Designer: $175K+/-*
Cost Estimator: $5K
Bid Hosting: $10K+/-
Advertising: $2K+/-
TOTAL: $347K?**
* Listed OPM fee includes additional (1) month of design (March 2022), additional (1) month of bidding (June 2022) and additional strategizing months (currently August – September) | $50K+/-
** Additional contingency and construction / bid overage not included **
*** The above values exclude construction – closeout as those phases are part of the existing OPM & Designer contracts ***
NOV-DEC
JAN-FEB
APRIL 2023 – MAY 2024
JUNE - JULY
Docs & Prequal
STM
Bid
MARCH
Construction
Closeout

## Slide 10
Option 2A: Re-Design, Re-Prequal & Re-Bid to Existing Budget Timeline and Costs
NOV 2022 – OCT 2023
NOV-DEC
FEB 2024 – MARCH 2025
APRIL - MAY
Prequal
Bid
JAN
Construction
Closeout
Design
Prequal
STM
OPM: $340K+/-*
Designer: $1.4M+/-
Cost Estimator: $28K
Bid Hosting: $10K+/-
Advertising: $2K+/-
TOTAL: $1.8M+/-?**
* Listed OPM fee includes additional (1) month of design (March 2022), additional (1) month of bidding (June 2022) and additional strategizing months (currently August – September) | $50K+/-
** The above values exclude construction – closeout as those phases are part of the existing OPM & Designer contracts ***